## 2023 (Goal 1)
GOAL | OBJECTIVE | 2023 PERFORMANCE STANDARDS OBJECTIVES | DUE | STANDARDS MET? | ACTIONS TAKEN/COMMENTS
GOAL 1: PROVIDE THE MOST EFFICIENT USE OF GROUNDWATER | MAINTAIN A WELL REGISTRATION PROCESS (8.1.1)
| The CCGCD require all exempt and non-exempt wells to be registered with the Disrict and has the authority to impose fines against those who do not register their wells. Also, it is a violation of District rules for drillers and pump installers to work on a well that is not registered with the District. District staff will at least twice annually report to the Board the number of well registrations to date and the number of violations and associated fines for failure to register or working on wells not registered. | Provide the number of reports on well registrations to the Board each year. | At least twice in 2023 and during Annual Report meeting | Yes | GM reported on well registrations during the February and July Board meetings. An additional update will be provided during the Annual Report presentation.
|  | Provide the number of well registrations to the Board each year. | At least twice in 2023 and during Annual Report meeting | Yes | By year-end 2023, there were 5,895 total well registrations with the District. 165 new well registrations were received in 2023.
|  | Provide the number of registration violations and the associated fines to the Board each year. | At least twice in 2023 and during Annual Report meeting | Yes | Two warnings were issued regarding registration violations in 2023, bute no fines assessed in 2023. $400 of fines were collected in January for registration violations from the prior year.
MAINTAIN A WELL PERMITTING PROCESS (8.1.2)
| The CCGCD requires all active non-exempt wells be permitted with the District. CCGCD staff will disclose to the Board at least twice annually, the number of permit applications, the number of permits granted and the number of permits pending. During these reports, staff will also report the associated total permitted amount. The District will impose fines as necessary to ensure adherence to District rules regarding permitting requirements. Staff will report the number of permit violations and associated fines. | Provide the number of reports regarding permitting. | At least twice in 2023 and during Annual Report meeting | Yes | Reports provided to Board in January and July 2023 and during review of Annual Report in early 2024.
|  | Provide the number of permit applications received and permits granted each year. | At least twice in 2023 and during Annual Report meeting | Yes | 26 new permit applications or major amendments were received and 26 were granted in 2023. Of those granted, 14 were Class A, five were Class B and seven were Class C.
|  | Provide the permit volume for permits granted. | At least twice in 2023 and during Annual Report meeting | Yes | Total volume of new permits is 9,331.2 ac-ft. Of this, 205.0 ac-ft were assgined to Class A permits, 1,340.4 ac-ft to Class B permits and 7,785.8 ac-ft to Class C permits.
|  | Provide the number of permits pending at year-end. | By 12/31/2023 or during Annual Report meeting | Yes | There were no pending permit applications at year end.
|  | Provide the number and amount of fines imposed each year as a result of failure to permit. | By 12/31/2023 or during Annual Report meeting | Yes | No violations or fines were assessed for failure to permit a well in 2023.
MAINTAIN A WELL METERING PROGRAM AND ENFORCE RULES REGARDING WATER USAGE REPORTING (8.1.3)
| CCGCD requires that Class C permit holders (wells with the capacity to pump more than 600 gpm) install meters on their wells unless exempted by the CCGCD Board. Additionally, permit holders are required to report water usage annually at year end. CCGCD has authority to impose fines against those who fail to meter their wells as stipulated or to report usage within the required timeframe. | Provide number of wells required to be metered and the number acutally metered. | By 12/31/2023 or during Annual Report meeting | Yes | The District requires 213 wells to be equipped with meters. At year-end 2023, 196 have been installed. Some wells in process of changing out meters. 11 wells were voluntarily metered.
|  | Provide the number of violations and total fines assessed as a result for not metering as stipulated by rules. | By 12/31/2023 or during Annual Report meeting | Yes | No violations and no fines have been assessed for not metering as stipulated by rules in 2023.
|  | Provide the number of violations and total fines assessed for failure to report water usage. | By 12/31/2023 or during Annual Report meeting | Yes | No violations or fines have been assessed for failure to report water usage in 2023.

## 2023 (Goal 2)
GOAL | OBJECTIVE | 2023 PERFORMANCE STANDARDS OBJECTIVES | DUE | STANDARDS MET? | ACTIONS TAKEN/COMMENTS
GOAL 2: CONTROLLING AND PREVENTING WASTE OF GROUNDWATER | SET AND ENFORCE SPACING REQUIREMENTS AND PUMPAGE REGULATIONS (8.2.1)
| In order to minimize the potential for waste of groundwater resources, the CCGCD shall mandate minimum spacing regulations from water production wells from property lines and from each other. For non-exmpt wells, spacing from existing wells shall be defined by the pumpage rate put forth in the permit application. The CCGCD also clearly establishes on the permit a maximum amount to be pumped over the course of the permit period. District staff will investigate and report to the Board all instances where spacing regulations were not followed and where pumpage exceeded the amount allowable. | Provide the number of violations and total fines assesed from failure to adhere to spacing requirements. | By 12/31/2023 or during Annual Report meeting | Yes | In 2023, no violations occurred and no fines were assessed for failure to adhere to District-mandated spacing requirements.
|  | Provide the number of violations and total fines assessed from failure to adhere to pumping allowances. | By 12/31/2023 or during Annual Report meeting | Yes | One violation occurred for failure to adhere to pumping allowance (in 2022) and $500 fine was assessed. Shall review later after all water usage reports for 2023 received.
MAINTAIN A WATER WELL INSPECTION PROGRAM FOR NON-EXEMPT WELLS (8.2.2)
| The District will monitor and communicate to well owners any indications of inefficiency in well operations that might cause waste of groundwater as defined in Management Plan. CCGCD staff will report to the Board at least annually, the number of site visits to check equipment and the number of notices and violations of District rules regarding waste. | Provide the number of site visits to inspect wells. | By 12/31/2023 or during Annual Report meeting | Yes | Two site visits occurred during 2023.
|  | Provide the number of notices and violations of District rules regarding well maintenance and/or groundwater waste. | By 12/31/2023 or during Annual Report meeting | Yes | No violations or notices were sent regarding lack of well maintenance or groundwater waste in 2023
DISSEMINATE INFORMATION ON WASTE PREVENTION (8.2.3)
| In conjunction with efforts in water conservation, the CCGCD will implement a waste prevention program with the purpose of educating constituents of the District on ways to prevent waste of groundwater. The District staff at least once annually shall give notice to the public of ways to prevent waste in one or more of the following ways: updates on the District website or District Facebook page; presentations to civic or governmental groups; articles in newspapers or newsletters; or by making available appropriate brochures. | Provide the number ways the District provided notice to the public on how to prevent waste of groundwater. | By 12/31/2023 or during Annual Report meeting | Yes | In 2023, the District provided notice to the public of ways to prevent waste by the following: 1) through multiple posts on the District Facebook page regarding prevention of waste; 2) through civic presentations; and 3) through a brochures entitled "Texas Lawn Water Guide" and a second brochure that addressed runoff, evaporation, underwatering and overwatering that were made available at the District office.

## 2023 (Goal 3)
GOAL | OBJECTIVE | 2023 PERFORMANCE STANDARDS OBJECTIVES | DUE | STANDARDS MET? | ACTIONS TAKEN/COMMENTS
GOAL 3: ADDRESSING CONJUNCTIVE SURFACE WATER MANAGEMENT ISSUES | PARTICIPATION IN REGIONAL PLANNING PROCESSES (8.3.1)
| CCGCD is wholly within the Lower Colorado River Planning Group (Region K). Each year that the regional water planning process is underway, the District will attend at least one Region K meeting. | Provide the number of Region K meetings held and attended by a District representative each year. | By 12/31/2023 or during Annual Report meeting | Yes | The GM attended 5 out of 5 Region K meetings and has attended 2 Region K committee meeting in 2023.
WORK WITH LCRA TO PROMOTE POSTIIVE CONJUNCTIVE WATER MANAGEMENT PROJECTS (8.3.2)
| The CCGCD will work with LCRA and appropriate government agencies to advance projects that might protect and/or supplement groundwater resources in the area. To help accomplish this, District staff will routinely monitor LCRA conjunctive water projects that might impact CCGCD and report the appropriate news to the Board at least twice annually. | Provide the number of updates to the CCGCD Board regarding LCRA conjunctive use projects. | At least twice in 2023 | Yes | Reports were provided at each of the seven meetings on the status of LCRA Highland Lake levels. One update for proposed LCRA reservoirs was provided in January.
IDENTIFY AND ADDRESS LEGISLATIVE POLICIES THAT MIGHT AFFECT GROUNDWATER RESOURCES (8.3.3)
| CCGCD staff regularly uses TAGD as a means to monitor Texas State legislative and judicial activity regarding groundwater issues. Staff will present to the Board at least twice annually while the Texas legislature is in session, updates on legislative and judicial activities that may impact CCGCD constituents. The Board will pass resolutions, as needed, to help influence the formulation of legislative policies that might positivley impact the District. | Provide the number of updates to the CCGCD Board of groundwater related legislative policies. | At least twice in 2023 | Yes | Legislative updates have been provided in January, July and December.
|  | Provide the total number of resolutions passed by the Board and/or testimonies given that were meant to influence legislative policy. | As needed | Yes | In 2023, the Board passed three resolutions. No testimonies were given that were meant to influcence legislative policy.

## 2023 (Goal 4)
GOAL | OBJECTIVE | 2023 PERFORMANCE STANDARDS OBJECTIVES | DUE | STANDARDS MET? | ACTIONS TAKEN/COMMENTS
GOAL 4: ADDRESSING NATURAL RESOURCE ISSUES | ESTABLISH AND MAINTAIN A WATER-QUALITY MONITORING PROGRAM (8.4.1)
| The CCGCD will maintain a water-quality monitoring network. Additionally, CCGCD will act on all reasonable requests from consitutuents involving wter quality concedrns. The CCGCD staff will report to the Board at least once annually, the number of samples collected and analyzed and a synopsis of hte associated results. | Provide the number of water-quality monitoring wells | By 12/31/2023 or during Annual Report meeting | Yes | In 2023, water quality samples taken from approximately 49 public supply wells in Colorado County. A water-quality database has been developed for the District which will include access to over 150 wells in Colorado County. Expect to be operational in 2024.
|  | Provide the number of samples collected and analyzed | By 12/31/2023 or during Annual Report meeting | Yes | In 2023, the State collected and analyzed approximately 847 water samples (not countying negative coliform tests).
|  | Provide a synopsis of water qualtiy test results highlighting any areas where contamination has been reported or discovered | By 12/31/2023 or during Annual Report meeting | Yes | In 2023, no samples were flagged as potentially contaminated or hazardous. Coliform bacteria found in test sampels from two water systems (municipal or poublic supply).
|  | Provide the number of actions taken regarding water quality issues submitted by constituents | By 12/31/2023 or during Annual Report meeting | Yes | In 2023, four constituents inquired about testing their groundwater. Constituents were directed to contact the Colorado County AgriLife Extension Office.
ENFORCE PROPER MAINTENANCE OF SUSPENDED WELLS AND ENCOURGE PLUGGING OF ABANDONED WELLS (8.4.2)
| The CCGCD may inspect suspended and abandoned wells to ensure proper closing of wells in accordance to rules set forth by CCGCD. Notices will be sent and fines may be asessed against well owners whose wells do not adhere to District Rules. In order to incentivize well owners with abandoned wells to plug them, the District will maintain a rebate program whereby well owners can recover some of the cost of plugging their wells. | Provide the number of notices sent out and possible fines assessed to well owners or operators concerning violations of District rules concerning proper closure of abandoned or suspended wells | By 12/31/2023 or during Annual Report meeting | Yes | In 2023, no notices or fines were assessed due to failure to properly close or plug abandonded or suspended wells.
|  | Provide the number of wells plugged each year | By 12/31/2023 or during Annual Report meeting | Yes | In 2023, two plugging reports were submitted to the District.
|  | Provide the number of plugging assistance requests each year | By 12/31/2023 or during Annual Report meeting | Yes | In 2023, the District received no plugging assistance requests. Notices of the District rebate program were routinely posted on the District Facebook page.
|  | Provide the annual amount of District money rebated to well owners requesting well plugging assistance | By 12/31/2023 or during Annual Report meeting | Yes | In 2023, no District funds were rebated to well owners.
MONITORING MINING AND OIL & GAS COMPANY OPERATIONS (8.4.3)
| CCGCD staff will monitor the Texas Railroad Commission (RRC) and other appropriate databases to determine any new locations of salt water disposal wells and the location of wells that are being hydraulically fracture stimulated. District staff will also monitor new gravel mining operations. CCGCD staff will report to the Board at least annually, any new salt water or waste disposal wells in Colorado County, any wells scheduled for fracking and any new gravel operations. The CCGCD staff will further report any violations for failure to permit groundwater wells in support of hydraulic fracking operations. | Provide the number of new salt water or waste water disposal or injection wells in Colorado County | By 12/31/2023 or during Annual Report meeting | Yes | In 2023, no salt water disposal wells were permitted or planned in Colorado County.
|  | Provide the number of groundwater wells being used to support fracking operations | By 12/31/2023 or during Annual Report meeting | Yes | Usage of the EOG well in northern Colorado County, permitted for fracking, is ongoing. No additional water wells were permitted for fracking operations in 2023.
|  | Provide the number of violations for failure to permit wells being used in support of fracking operations | By 12/31/2023 or during Annual Report meeting | Yes | In 2023, there were no violations for failure to permit wells used in support of fracking operations.
|  | Provide the number of new gravel mining operations in Colorado County | By 12/31/2023 or during Annual Report meeting | Yes | In 2023, no new wells were permitted in support of new mining operations.

## 2023 (Goal 5)
GOAL | OBJECTIVE | 2023 PERFORMANCE STANDARDS OBJECTIVES | DUE | STANDARDS MET? | ACTIONS TAKEN/COMMENTS
GOAL 5: ADDRESSING DROUGHT CONDITONS | COLLECT AND REVIEW DROUGHT CONDITION INFORMATION (8.5.1)
| CCGCD will track information on weather, precipitation and drought data on the TWDB drought page and other key sites and post key information and links on the District website and/or Facebook page at least twice a year. | Provide an update to the CCGCD website to reflect the latest drought index and precipitation totals. | At least twice in 2023 | Yes | A link has been provided on the District website to the Texas Drought Index which is typically updated weekly. A link has been provided to TexMesonet which provides precipitation totals. Addtionally, postings on TexMesonet and the TWDB "Water Weekly", which shows Texas drought conditions across the State, is posted periodicallly on the District Facebook page.

## 2023 (Goal 6)
GOAL | OBJECTIVE | 2023 PERFORMANCE STANDARDS OBJECTIVES | DUE | STANDARDS MET? | ACTIONS TAKEN/COMMENTS
GOAL 6: ADDRESSING CONSERVATION, RAINWATER HARVESTING AND BRUSH CONTROL | PROTECT EXEMPT USAGE FROM HIGH CAPACITY WELLS (8.6.1)
| District staff shall enforce the following District rules that were implemented to protecy offset usage: requiring high capacity wells to be screened in deeper intervals; requiring offset high capcity wells to be spaced a sufficient distance away from exempt wells; and, requiring permit applications requesting more than 1000 ac-ft average annual pumpage to provide a conservation plan. Violations will be reported to the Board as they occur. | Provide the number of violations and associated fines regarding spacing rules. | By 12/31/2023 or during Annual Report meeting | Yes | In 2023, no violations or fines were assessed regarding spacing rules.
|  | Provide the number of violations and associated fines regarding failure to adhere to minimum screening depths. | By 12/31/2023 or during Annual Report meeting | Yes | In 2023, no violations or fines were assessed regarding minimum screening depths.
|  | Provide the number of hydrogeological studies, mitigations plans and conservation reports required by the District. | By 12/31/2023 or during Annual Report meeting | Yes | In 2023, no new hydrogeological studies, mitigation plans, etc. were required by the District. The threshold for requiring a hydrogeological study was changed in 2023.
ESTABLISH A PROGRAM TO EMPHASIZE WATER CONSERVATION (8.6.2)
| In coordination with efforts in waste prevention, the CCGCD will implement a conservation program with the purpose of educating the constituents of the District on ways to conserve water. The District staff at least once annually shall give notice to the public of ways to conserve water in one or more of the following ways: updates on the District website or District Facebook page; presentations to civic or governmetnal groups; articles in newspapers or newsletters; or by making available appropriate brochures. | Provide the number of ways the District provided notice to the public on how to conserve water. | Once in 2023 | Yes | In 2023, the District provided notice to the public of ways to conserve water by the following: 1) through multiple posts on the District Facebook page and maintaining a "Conservation" tab on the District's website; 2) through civic presentation; and, 3) through brochures made available in the office.
MONITOR POTENTIAL WAYS TO EMPHASIZE RAINWATER HARVESTING AND BRUSH CONTROL (8.6.3)
| The CCGCD staff will keep abreast of brush control and rainwater harvesting techniques and make that information available at least once annually, to the constitutents of the District through brochures, Facebook announcements or website links. | Provide the number of ways the District provided notice to the public on how to go about brush control and/or rainwater harvesting. | Once in 2023 | Yes | In 2023, the District provided notice to the public on methods for brush control and/or rainwater harvesting by the following: 1) through multiple posts to the District Facebook page regarding rainwater harvesting; 2) through presence of a brochure in the District office entitled "Texas Manuel for Rainwater Harvesting".

## 2023 (Goal 7)
GOAL | OBJECTIVE | 2023 PERFORMANCE STANDARDS OBJECTIVES | DUE | STANDARDS MET? | ACTIONS TAKEN/COMMENTS
GOAL 7: ADDRESSING THE DESIRED FUTURE CONDITIONS | MAINTAIN A WATER LEVEL MONITORING PROGRAM (8.7.1)
| The CCGCD will maintain a District water-level monitoring network of at least 15 wells. The depth to the water level will be measured at least annually and results will be recorded in the District's database. The CCGCD Board will be updated on key monitor wells at least twice a year. | Provide the number of District monitor wells and the number of monitor wells measured at least once annually. | By 12/31/2023 or during Annual Report meeting | Yes | In 2023, all 15 active District monitor wells have been measured at least once.
|  | Provide the number of updates to the Board on key monitor wells. | At least twice in 2023 | Yes | Updates on water levels of key wells have been provided to the Board at seven meeting held in 2023.
ANALYZE WATER LEVEL DATA FOR ADHERENCE TO DFC (8.7.2)
| At least once a year, charts will be constructed of each CCGCD monitor well showing the changes in water level through time. The data and charts for the CCGCD monitor wells will be updated on the Distrcit website at least annually. The District will also chart TWDB monitor wells within Colorado County. At least once annually, this data will be assimilated to determine compliance with the desired future conditions (DFC) of the Gulf Coast Aquifer in Colorado County. | Provide the number of graphic displays (charts) generated for CCGCD monitor wells. | By 12/31/2023 or during Annual Report meeting | Yes | Depth to water level and water level elevation charts for all 15 active monitor wells were actively revised as new measurements are taken in 2023.
|  | Provide the number of District website updates of CCGCD monitor well data. | By 12/31/2023 or during Annual Report meeting | Yes | All water level measurements noted above have been updated on the District's website each month. Inactive District monitor wells are also available on the District website.
|  | Provide a comparison of water level changes from monitor wells to the CCGCD DFC. | By 12/31/2023 or during Annual Report meeting |  | DFC measurements are made after year end.